## Blad1
fase | activiteiten | wie (takenverdeling) | uren geschat | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | week 13 | week 14 | week 15 | week 16 | week 17 | week 18 | week 19 | week 20
1 | pakket van eisen h3 .5 | Zakaria | 1 | week 1: is klaar
2 | plan van aanpak (PvA) | Samen | 1 | week 1: vw klaar
3 | ontwerp (FO) | Samen | 1 | week 1: vw klaar
3.1 | functioneel ontwerp | Martijn | 4 | week 1: vw klaar
3.2 | technisch ontwerp | Samen | 5 | week 2: vw klaar
4 | realiseren
| wens 1 | Zakaria | 4 | week 2: vw klaar
| wens 2 | Melji | 3 | week 2: vw klaar
| wens 3 | Justin | 4 | week 3: vw klaar
| wens 4 | Martijn | 2 | week 3: vw klaar
| wens 5 | Tim | 4 | week 4: vw klaar
| wens 6 | Martijn | 3 | week 4: vw klaar
| wens 7 | Tim | 5 | week 5: vw klaar
| wens 8 | Samen | 4 | week 5: vw klaar
| wens 9 | Samen | 4 | week 6: vw klaar
| wens 10 | Samen | 3 | week 6: vw klaar
| wens 11 | Samen | 3 | week 6: vw klaar
5 | test
| wens 1 | Melji | 1 | week 2: vw klaar
| wens 2 | Zakaria | 1 | week 2: vw klaar
| wens 3 | Martijn | 1 | week 3: vw klaar
| wens 4 | Tim | 1 | week 3: vw klaar
| wens 5 | Justin | 1 | week 4: vw klaar
| wens 6 | Justin | 1 | week 4: vw klaar
| wens 7 | Zakaria | 1 | week 5: vw klaar
| wens 8 | Melji | 1 | week 5: vw klaar
| wens 9 | Martijn | 1 | week 6: vw klaar
| wens 10 | Martijn | 1 | week 6: vw klaar
| wens 11 | Justin | 1 | week 6: vw klaar